## Instructions
INDUSTRY ACADEMIA COMMUNITY
DOMAIN NAME: | Cloud Computing
INTERN NAME: | Piyush Raj Kumar
PROJECT NAME: | MongoSafenet
DOCUMENT NAME: | Lessons Learnt Log
CREATED ON: | 23- 08 -2023
Purpose of Document
Lessons Learned Logs are used to capture and share knowledge about what has worked well and what could have been done differently during the planning, management and delivery of an improvement project.
They help others learn from the project team's experience. Lesson Learned Logs: Help support a learning culture.
INSTRUCTIONS:
1. Text in Italics are instructions for completing the document
2. Text in orange is just for reference and should be deleted before submitting the document
3. Comments may be added to some of the cells, please read the comments to better understand the terms
4. All fields must be duly filled
5. The descriptions for what to be filled in each of the fields are provided in the template.
6. Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes.

## LESSONS LEARNED
LESSONS LEARNED
DOCUMENT VERSION: 1.0
| PROJECT NAME | MongoSafenet
| PROJECT ID | Cloud Computing
| PROJECT MANAGER | Harshada Topale
| PROJECT SPONSOR | Tushar Topale
SL. NO | DATE RAISED | EVENT | LESSON CATEGORY | EARLY WARNING SIGNS? | RECOMMENDATIONS | ACTIONS | OWNER | STATUS | ADDITIONAL COMMENTS
| MENTION THE DATE ON WHICH THE MATTER WAS RAISED | DESCRIBE THE EVENT THAT WAS RAISED | MENTION WHICH CATEGORY THE EVENT WAS RELATED TO | MENTION YES OR NO | MENTION THE RECOMMENDATIONS THAT WAS SUGGESTED FOR SOLVING THE EVENT IF ANY | MENTION THE ACTION SELECTED FOR SOLVING THE VENT | MENTION THE RESPONSIBLE PERSON FOR SOLVING THE EVENT | SOLVED/ PENDING | MENTION IF ANYTHING ELSE OCCURRED DURING THE TIME OF THE MENTIONED EVENT
1 | 2023-08-21 | MongoDb Daemon Process | Handling Background Operations of Mongodb | NO | Official Mongodb Docs & StackOverflow | Run "mongod" in Command Prompt | Piyush Raj Kumar | SOLVED | Without it Connection with mongodb can't be established
2 | 2023-08-29 | Not Installed mongodb Dependencies needed for the Script | Important for Working of the Script | NO | Official Mongodb Docs & Google | Download MongoDb Cli Database Tools (msi) | Piyush Raj Kumar | SOLVED | Script Won't work without it.
3 | 2023-09-03 | Uniqueness Of the Backup | TO AVOID CLUTTER of Scheduled Backups | YES | Google, StackOverflow & Youtube Learning | Changing the Script By Adding Current TIMESTAMP as the backup folder name | Piyush Raj Kumar | SOLVED | Crucial Step as later it needeed to be uploaded on AWS S3 & Remove it from local directory.
4 | 2023-09-05 | Connect PC To AWS Cloud | To Take Backups On Cloud | YES | Google & AWS Docs | Installing AWS Cli | Piyush Raj Kumar | SOLVED
5 | 2023-09-07 | Accessing the AWS S3 Using aws configre in cli | For uploading the Backup On S3 | YES | AWS Docs | Creating AWS Free Tier Account. | Piyush Raj Kumar | SOLVED | Else there is no Other ways found Like a Aws Account Labs
6 | 2023-09-11 | Working POC To be accessible when needed anywhere | For Accessing S3 not as Root User as for account Security | NO | AWS Docs | Creating an IAM User for Access Key & Secret Key | Piyush Raj Kumar | SOLVED
7 | 2023-09-22 | Scheduling Backups | Automatic Mongodb Backups | YES | Google, StackOverflow & Youtube | CRONS METHOD instead of Windows Task Scheduler | Piyush Raj Kumar | SOLVED | Crons are used in Aws EC2 (Ubuntu Version)