## Guide
IAC INTERNSHIP PROGRAM 2023
DOCUMENT TITLE: | PROJECT SCHEDULE
Document created By: | PIYUSH RAJ KUMAR
Document Created On: | 16-08-2023
Version: | 1
Instructions:
1. Create a project schedule based on your Work Breakdown structure
2. You may refer the 'Example' tab. Activities & Task to be included in the schedule will vary based on your selected domain
3. You may group/ expand/collapse the set of activities
4. Please rename the file as 'IAC IP23 - your Domain Name - Project Schedule - Your Full Name'

## Project Schedule
IAC Internship Program 2023 - CLOUD COMPUTING Project Schedule
|  | PROJECT START DATE |  | 2023-08-03
|  | Display Week Sr No |  | 1 | [9 empty] | 2023-07-31 | [6 empty] | 2023-08-07 | [6 empty] | 2023-08-14 | [6 empty] | 2023-08-21 | [6 empty] | 2023-08-28 | [6 empty] | 2023-09-04 | [6 empty] | 2023-09-11 | [6 empty] | 2023-09-18 | [6 empty] | 2023-09-25
 | time axis 2023-07-31 to 2023-10-01
Sr No | Week/ Duration/ Sprint/ Phase | Activities | Task | Sub Task | Dependencies | Assigned to | Start Date | End Date | Actual End Date | Hours required | Status | Progress | Comments | time axis 2023-07-31 to 2023-10-01
1 | Week 1 | Initiation | Project Kickoff | Define project scope | - | Piyush Raj Kumar | 2023-08-02 | 2023-08-03 | 2023-08-03 | 3 | Completed | 100% | Initial project setup
1.1 |  |  |  | Identify business problem | - | Piyush Raj Kumar | 2023-08-03 | 2023-08-03 | 2023-08-03 | 2 | Completed | 100% | Business problem identified
1.2 |  |  |  | Create a project charter | 1.1 | Piyush Raj Kumar | 2023-08-04 | 2023-08-05 | 2023-08-06 | 3 | Completed | 100% | Project charter creation planned
1.3 |  |  |  | Requirement gathering | 1.2 | Piyush Raj Kumar | 2023-08-07 | 2023-08-14 | 2023-08-14 | 3 | Completed | 100% | Requirement gathering planned
1.4 |  |  |  | Creating SRS Document | 1.3 | Piyush Raj Kumar | 2023-08-10 | 2023-08-13 | 2023-08-13 | 2 | Completed | 100% | SRS Document creation planned
2 | Week 2 | Planning | Approval of business process | - | - | Piyush Raj Kumar | 2023-08-14 | 2023-08-14 | 2023-08-14 | 1 | Completed | 100% | Business process approval planned
2.1 |  |  | Baseline project plan | - | 1.4 | Piyush Raj Kumar | 2023-08-14 | 2023-08-15 | 2023-08-15 | 4 | Completed | 100% | Baseline project plan creation planned
2.2 |  |  |  | Work Breakdown Structure | 2.1 | Piyush Raj Kumar | 2023-08-15 | 2023-08-16 | 2023-08-16 | 3 | Completed | 100% | WBS creation planned
2.3 |  |  |  | Project Schedule | 2.2 | Piyush Raj Kumar | 2023-08-16 | 2023-08-20 | 2023-08-20 | 6 | Completed | 100% | Project schedule creation planned
2.4 |  |  |  | RAID Logs | 2.3 | Piyush Raj Kumar | 2023-08-18 | 2023-09-23 | 2023-09-25 | 4 | Completed | 100% | RAID Logs creation planned
3 | Week 3 | Execution | Design | - | - | Piyush Raj Kumar | - | - | - | - | Completed | 100% | Design phase begins
3.1 |  |  |  | Design Specification | 2.4 | Piyush Raj Kumar | 2023-08-21 | 2023-08-22 | 2023-08-22 | 4 | Completed | 100% | Design specification planned
3.1.1 |  |  |  | - Research | 3.1 | Piyush Raj Kumar | 2023-08-22 | 2023-08-24 | 2023-08-24 | 8 | Completed | 100% | Research planned
3.1.2 |  |  |  | - Analyze | 3.1.1 | Piyush Raj Kumar | 2023-08-24 | 2023-08-25 | 2023-08-25 | 3 | Completed | 100% | Analysis planned
3.1.3 |  |  |  | - Design | 3.1.2 | Piyush Raj Kumar | 2023-08-25 | 2023-08-26 | 2023-08-26 | 4 | Completed | 100% | Design planned
3.2 |  |  |  | Test Plan | 3.1.3 | Piyush Raj Kumar | 2023-08-26 | 2023-08-26 | 2023-08-27 | 3 | Completed | 100% | Test plan creation planned
4 | Week 4 | Develop |  | - | - | Piyush Raj Kumar | - | - | - | - | Completed | 100% | Development phase begins
4.1 |  |  |  | Scripting | 3.2 | Piyush Raj Kumar | 2023-08-28 | 2023-08-31 | 2023-08-31 | 8 | Completed | 100% | Scripting planned
4.2 |  |  |  | Connection String | 4.1 | Piyush Raj Kumar | 2023-08-31 | 2023-09-01 | 2023-09-02 | 2 | Completed | 100% | Connection String planned
4.3 |  |  |  | MongoDB backup | 4.2 | Piyush Raj Kumar | 2023-09-03 | 2023-09-04 | 2023-09-04 | 3 | Completed | 100% | MongoDB backup planned
4.4 |  |  |  | Upload to AWS S3 bucket | 4.3 | Piyush Raj Kumar | 2023-09-05 | 2023-09-06 | 2023-09-08 | 7 | Completed | 100% | Upload to S3 planned
4.5 |  |  |  | Clean Local Backup | 4.4 | Piyush Raj Kumar | 2023-09-08 | 2023-09-09 | 2023-09-09 | 2 | Completed | 100% | Clean Local Backup planned
5 | Week 5 | Testing |  | - | - | Piyush Raj Kumar | - | - | - | - | Completed | 100% | Testing phase begins
5.1 |  |  |  | Manual testing | 4.5 | Piyush Raj Kumar | 2023-09-11 | 2023-09-12 | 2023-09-12 | 4 | Completed | 100% | Manual testing planned
5.2 |  |  |  | Automation testing | 5.1 | Piyush Raj Kumar | 2023-09-13 | 2023-09-13 | 2023-09-13 | 2 | Completed | 100% | Automation testing planned
5.3 |  |  |  | Test Results | 5.2 | Piyush Raj Kumar | 2023-09-13 | 2023-09-14 | 2023-09-14 | 2 | Completed | 100% | Test result analysis planned
6 | Week 6 | Deploy |  | - | - | Piyush Raj Kumar | - | - | - | - | Completed | 100% | Deployment phase planned
6.1 |  |  |  | Video | 5.3 | Piyush Raj Kumar | 2023-09-15 | 2023-09-20 | 2023-09-22 | 11 | Completed | 100% | Video creation planned
6.2 |  |  |  | Installation Guide | 6.1 | Piyush Raj Kumar | 2023-09-19 | 2023-09-22 | 2023-09-22 | 9 | Completed | 100% | Installation guide creation planned
7 | Week 7 | Closure |  | - | - | Piyush Raj Kumar | - | - | - | - | Completed | 100% | Closure phase begins
7.1 |  |  |  | Lessons Learned | 6.2 | Piyush Raj Kumar | 2023-08-23 | 2023-09-25 | 2023-09-22 | 3 | Completed | 100% | Lessons learned documentation planned
7.2 |  |  |  | Project Report & Submission | 7.1 | Piyush Raj Kumar | 2023-09-25 | 2023-09-27 | 2023-09-27 | 8 | Completed | 100% | Project report creation planned
Note on H7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Nirbhey Singh Pahwa - I was thinking if we should add an actual start date column as well? Reply: Or, let's call this one as planned start date and the next one as start date. The same can be done for End date. Because, writing 'actual' feels as if we've missed some deadline of some sorts so can be avoided. You can have this in the DM Goals template for now, let me add this to the next version of this template, i.e., Goals [Template v0.5] Thank you

## Project Plan
PROJECT PLAN
DOCUMENT VERSION: 1.0
PROJECT NAME | MongoSafenet
PROJECT MANAGER | Harshada Topale
PROJECT DELIVERABLE | Project Guide + Scripts + Video + Documents
PROJECT SCOPE | Automate MongoDb Backups
PROJECT START DATE | 2023-08-03
PROJECT END DATE | 2023-09-28
OVERALL PROGRESS | Completed
SL NO | TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION IN DAYS | STATUS
1 | 1 Initiation
1.1 | 1.1 Identify business problem | Piyush Raj Kumar | 2023-08-03 | 2023-08-03 | - | COMPLETED
1.2 | 1.2 Create a project charter | Piyush Raj Kumar | 2023-08-04 | 2023-08-06 | 2 | COMPLETED
1.3 | 1.3 Requirement gathering | Piyush Raj Kumar | 2023-08-07 | 2023-08-14 | 2 | COMPLETED
1.4 | 1.4 Creating SRS Document | Piyush Raj Kumar | 2023-08-10 | 2023-08-13 | 3 | COMPLETED
2 | 2 Planning
2.1 | 2.1 Approval of business process | Piyush Raj Kumar | 2023-08-14 | 2023-08-14 | - | COMPLETED
2.2 | 2.2 Baseline project plan | Piyush Raj Kumar | 2023-08-14 | 2023-08-15 | 1 | COMPLETED
2.3 | 2.3 Work Breakdown Structure | Piyush Raj Kumar | 2023-08-15 | 2023-08-16 | 1 | COMPLETED
2.4 | 2.4 Project Schedule | Piyush Raj Kumar | 2023-08-16 | 2023-08-20 | 4 | COMPLETED
2.5 | 2.5 RAID Logs | Piyush Raj Kumar | 2023-08-18 | 2023-09-25 | 38 | COMPLETED
3 | 3 Execution
3.1 | 3.1 Design
3.1.1 | 3.1.1 Design Specification | Piyush Raj Kumar | 2023-08-21 | 2023-08-22 | 1 | COMPLETED
3.1.1.1 | 3.1.1.1 Research | Piyush Raj Kumar | 2023-08-22 | 2023-08-24 | 2 | COMPLETED
3.1.1.2 | 3.1.1.2 Analyse | Piyush Raj Kumar | 2023-08-24 | 2023-08-25 | 1 | COMPLETED
3.1.1.3 | 3.1.1.3 Logical Design | Piyush Raj Kumar | 2023-08-25 | 2023-08-26 | 1 | COMPLETED
3.1.2 | 3.1 .2 Test Plan | Piyush Raj Kumar | 2023-08-26 | 2023-08-27 | 1 | COMPLETED
3.2 | 3.2 Develop |  |  |  |  | COMPLETED
3.2.1 | 3.2.1 Scripting | Piyush Raj Kumar | 2023-08-28 | 2023-08-31 | 3 | COMPLETED
3.2.2 | 3.2.2 Connection String | Piyush Raj Kumar | 2023-08-31 | 2023-09-02 | 2 | COMPLETED
3.2.3 | 3.2.3 MongoDB backup | Piyush Raj Kumar | 2023-09-03 | 2023-09-04 | 1 | COMPLETED
3.2.4 | 3.2.4 Upload to AWS S3 bucket | Piyush Raj Kumar | 2023-09-05 | 2023-09-08 | 3 | COMPLETED
3.2.5 | 3.2.5 Clean Local Backup | Piyush Raj Kumar | 2023-09-08 | 2023-09-09 | 1 | COMPLETED
3.3 | 3.3 Testing
3.3.1 | 3.3.1 Manual testing | Piyush Raj Kumar | 2023-09-11 | 2023-09-12 | 1 | COMPLETED
3.3.2 | 3.3.2 Automation testing | Piyush Raj Kumar | 2023-09-13 | 2023-09-13 | - | COMPLETED
3.3.3 | 3.3.3 Test Results | Piyush Raj Kumar | 2023-09-13 | 2023-09-14 | 1 | COMPLETED
3.4 | 3.4 Deploy
3.4.1 | 3.4.1 Video | Piyush Raj Kumar | 2023-09-15 | 2023-09-22 | 7 | COMPLETED
3.4.2 | 3.4.2 Installation Guide | Piyush Raj Kumar | 2023-09-19 | 2023-09-22 | 3 | COMPLETED
4 | 4 Closure
4.1 | 4.1 Lessons Learnt | Piyush Raj Kumar | 2023-08-23 | 2023-09-22 | 30 | COMPLETED
4.2 | 4.2 Project Report | Piyush Raj Kumar | 2023-09-25 | 2023-09-27 | 2 | COMPLETED