## RAID LOG
| RAID Log | [9 empty] | Total | Critical | High | Moderate | Low | Negligible
[10 empty] | Risk | 6 | 0 | 0 | 0 | 0 | 0
| Project title: | MongoSafenet |  | Project Id: | Cloud Computing | Project Manager: | Harshada Topale |  |  | Assumption | 4 | 0 | 0 | 0 | 0 | 0
[10 empty] | Issue | 3 | 0 | 0 | 0 | 0 | 0
| DOCUMENT VERSION: | 1 |  | Last Updated date: | 2023-09-25 | Project Team Lead: | Piyush Raj Kumar |  |  | Dependency | 5 | 0 | 0 | 0 | 0 | 0
| Select … |  |  |  |  | Select … | Risk Priority Number | Open/Closed |  |  | 18 |  |  |  |  | 0
| RAID Category | Description | Impact | Mitigation | Owner | Priority | RPN (for risks) | Status
1 | Assumption | Availability of MongoDB Environment | Unavailability of database can disrupt backups. | Maintain MongoDB infrastructure reliability and redundancy. | Project Manager | Critical |  | Closed | Risk
2 | Assumption | AWS Infrastructure Readiness | Unprepared infrastructure can lead to project delays | Perform infrastructure readiness assessments before initiating the project. | Project Manager | High |  | Closed | Assumption
3 | Risk | Technical Complexity | Delays in implementation, potential errors, and increased project complexity. | Engage AWS experts for guidance, conduct thorough testing, and maintain clear documentation. | Project Manager | Low |  | Closed | Issue
4 | Risk | Data Security Breaches | Loss of sensitive data, legal consequences, damage to reputation. | Implement encryption and access controls, monitor security, and perform regular audits. | Project Manager | Moderate |  | Closed | Dependency
5 | Assumption | Stable Internet Connectivity | Connectivity issues can lead to data gaps. | Implement backup resumption mechanisms and monitor connectivity. | Project Manager | Low |  | Closed
6 | Issue | Technical Glitches | Backup failures, data inconsistency. | Rigorous testing, error-handling mechanisms, and automated alerts for issues. | Project Manager | High |  | Closed | Open
7 | Dependency | MongoDB Database | Database unavailability disrupts backups. | Ensure robust MongoDB infrastructure and proactive monitoring. | Project Manager | High |  | Closed | Closed
8 | Dependency | AWS Services | Service outages affect project functionality. | Monitor AWS service status, set up redundancy where feasible, and have contingency plans. | Project Manager | Low |  | Closed
9 | Issue | Data Loss or Corruption | Data integrity compromise, potential legal consequences. | Implement multiple backup copies, versioning, and robust error-checking. | Project Manager | Moderate |  | Closed | Critical
10 | Assumption | Cooperation for Testing | Delayed testing and potential user dissatisfaction. | Develop clear testing plans, communicate expectations, and provide user-friendly testing tools. | Project Manager | High |  | Closed | High
11 | Risk | Dependency on Third-Party Services | Service interruptions can disrupt backup processes and data availability. | Have backup plans, monitor AWS service status, and consider redundancy options. | Project Manager | Critical |  | Closed | Moderate
12 | Risk | Compatibility Issues | Disruption of existing processes and potential data loss. | Stay informed about updates, test compatibility with each change, and maintain version compatibility logs. | Project Manager | Critical |  | Closed | Low
13 | Risk | Performance Impact | Slower database operations and reduced user satisfaction. | Schedule backups during off-peak times, optimize backup scripts, and monitor resource utilization. | Project Manager | Low |  | Closed | Negligible
14 | Issue | Resource Constraints | Inability to scale with growing data. | Continuously monitor resource utilization, optimize storage strategies, and consider AWS service upgrades. | Project Manager | Low |  | Closed
15 | Dependency | Script Development | Inadequate scripts can lead to data loss or inconsistency. | Code reviews, version control, and regular script updates are essential. | Project Manager | Critical |  | Closed
16 | Dependency | User Cooperation | Delayed testing and suboptimal system configuration. | Maintain clear communication, user training, and incentives for cooperation. | Project Manager | Low |  | Closed
17 | Risk | User Adoption | Resistance to change, suboptimal system usage. | Provide user training, clear communication, and gather user feedback for improvements. | Project Manager | Low |  | Closed
18 | Dependency | Compliance | Non-compliance can result in legal consequences. | Engage legal experts, conduct compliance audits, and implement necessary controls. | Project Manager | High |  | Closed
19
20
21
22
23
24